What considerations should be made if you want to host the American Legion Riders Department of California (ALR DOC) West Coast Rally?

- Is there a local venue that can accommodate at least 200 to 300 people and is ADA compliant.

- Is there local lodging accommodations sufficient to host 200 to 300 people. This should include hotels, motels and RV’s.

- Can your Chapter/District commit to conducting all requirements listed in the Hosting Guidelines? This should be included in your minutes submitted to the DEC meeting preceding the West Coast Rally.

*************************************************************************************

To be considered to host the American Legion Riders State Rally a Chapter/District must:

1 YEAR PRIOR at DEC meeting prior to West Coast Rally:

  - Minutes from a Chapter/District meeting stating the Chapter/District had a motion, 2nd, discussion and voted in agreement to host the West Coast Rally 1 year out, including the year of rally to be hosted.

  - Chapter/District will put a rally committee in place no later than their next monthly meeting.

  - Minutes from a Post meeting stating the Chapter/District has informed the Post of its desire to host the ALRDEC West Coast Rally and the Post has voted in agreement to support the Chapter/District in hosting the ALRDEC West Coast Rally, including the year of rally to be hosted.

  - The hosting Chapter/District should report on a tentative location to host the West Coast Rally.

11 months out:

- Report to DEC a Chapter/District Rally Committee is in place, has the timeline list and is meeting and working on the requirements.

8 months out report to DEC:

- Confirm rally location. Must be able to hold a minimum of 200 to 300 persons, be ADA compliant and have suitable parking.

- If at a post, a letter from the post stating agreement on the Chapter/District hosting rally at the post, that they can accommodate the size of the rally and that the dates are clear on the post calendar.

- The hosting Post/Chapter/District will ensure event insurance is sufficient to cover the event. Acord form is to be available upon request.

- If at another venue, (shared veteran building or other), a letter from the venue stating the venue has agreed with the Chapter/District in hosting the rally on the agreed upon dates and any requirements the venue requires (money, insurance, etc.). If city involvement, a letter from them is also required with their requirements.

- If opportunity drawings, 50/50, etc. are being planned and donations for drawings are being worked on.

- How online registration will work and address for mail in registration.

- Cost of registration and what is included (i.e. shirts, pins, meals, etc.).

- Images of logos for flyers and merchandise have been previewed, completed and approved by Emblem Sales.

- Preview of rally flyer presented to ALRDEC.

5 months out report to DEC:

- List of accommodations, (hotels, motels, RV & camping), with reservation codes for each.

- What merchandise will be available.

1. To include what merchandise will be needed from the Quartermaster.

- Local law enforcement and city officials have been notified of upcoming convention, dates, etc. and are invited to opening ceremonies.

- Online registration open. Accepting mail in registration.

- Merchandise (i.e. wristbands, shirts, pins, hats, etc.) has been ordered.

- Opportunity drawing etc. donation progress.

- Meals have been decided on and there is a detailed plan for procurement.

3 months out report to DEC :

- Flyer or booklet which shows:

- Closest motorcycle repair shop(s) etc.

- Points of interest (in town and out) to visit

- Local medical facilities, and

- Local eateries if the venue isn’t hosting all meals.

The above should include: addresses, phone numbers, hours of operation with instructions, maps on how to get there.

1 month out:

- Report to DEC that merchandise has arrived.

- Report to DEC that prior reports in the timeline are still complete with no issues and all requirements are in place.

- Report to DEC, the DEC Convention and Rally and Chapter/District Rally Committee’s will continue to conduct weekly meetings.

60 days POST Rally report to DEC line item rally financial rundown:

- What was spent and made on merchandise. List each type of merchandise separately.

- What was spent and made on food. List breakfasts, lunch and dinners separately. List what was served at each meal. How much wasn’t used?

- What was spent and made on entertainment. List the types of entertainment for each day.

- What was spent and made on drawings, 50/50, etc.

- What was spent on venue rental?

- What was spent on permits?

- What was spent on insurance?

- What was spent on security?

- Was a shuttle service provided? Is so, what was cost?

- What was spent on office supplies?

- Was there online registration? Any cost?

Invite ALR DOC Convention & Rally Committee, President, Vice President, Sergeant-at-Arms & Secretary to all calls and face-to-face meetings.

All reports to the DEC will be given by the Convention and Rally Chairperson. This will require the Chairperson to have call in meetings with the Chapter/District’s convention/rally committee and the DEC convention committee together, monthly, to brainstorm ideas, put things in place, take care of any issues, etc.